WEEK 1 INTERNSHIP DELIVERABLE

Strategic Research & Planning in Agriculture Data Analysis

Research plan, data-source strategy, analytical methodology, timeline, resource allocation and risk assessment

Prepared for Internship Submission • 34-Hour Week 1 Scope

| Deliverable | Week 1 Strategic Research & Planning Report |
| --- | --- |
| Domain | Agriculture Data Analysis — India-focused with global benchmarks |
| Planned Workload | 34 hours |
| Primary Output | Submission-ready DOCX + organized supporting research package |

# Executive Summary

This Week 1 plan establishes a practical research and analytics framework for studying agricultural market trends, crop statistics and agribusiness developments using publicly available data. The strategy starts with authoritative Indian government sources and complements them with international datasets and research literature. The workflow moves from source discovery and data profiling to cleaning, exploratory analysis, market/crop trend analysis, validation and dashboard-ready outputs.

The plan prioritizes the Directorate of Economics & Statistics (ES&E/DES) of the Department of Agriculture and Farmers Welfare for official crop statistics and agricultural estimates; the Government of India's Open Government Data platform for machine-readable datasets; e-NAM for mandi-level price, arrivals and trade information; FAOSTAT for international comparability; World Bank indicators for macro/agricultural context; ICAR for research and technology developments; and MoSPI/NSS for agricultural-household and socio-economic context.

The Week 1 target is not to produce final business conclusions. It is to create a defensible research foundation: a source inventory, research-question framework, KPI dictionary, data-quality protocol, analysis plan, risk register and realistic 34-hour execution schedule.

# 1. Scope of the Research

## 1.1 In Scope

Indian crop area, production and yield trends by crop, state, district and season where available.

Agricultural commodity market behaviour: prices, arrivals, traded quantities and market-level variation.

Agribusiness context: production value, market integration, input/output trends, technology and research developments.

Seasonality, year-on-year changes, growth rates, volatility and geographic concentration.

Cross-source validation and documentation of definitions, units, coverage and update frequency.

Preparation of datasets and analytical specifications suitable for Python/SQL/Excel/Power BI or similar tools.

## 1.2 Out of Scope for Week 1

Building a production-grade forecasting model.

Making investment, procurement or policy recommendations from incomplete data.

Collecting proprietary farmer, retailer or company data.

Causal claims without an appropriate identification strategy and supporting variables.

Treating old or incomplete datasets as current without explicitly documenting their coverage period.

# 2. Strategic Objectives

| ID | Objective | Success criterion |
| --- | --- | --- |
| O1 | Build a reliable public-data source map | Identify authoritative sources, access method, granularity, frequency, coverage, licensing and limitations. |
| O2 | Define research questions | Translate broad agriculture topics into measurable questions that can be answered with public data. |
| O3 | Define KPIs and analytical metrics | Create a common measurement framework for crop performance, markets and agribusiness. |
| O4 | Design the data pipeline | Specify extraction, profiling, cleaning, validation, transformation and storage steps. |
| O5 | Plan analytical methods | Select descriptive, comparative, time-series, volatility, correlation and optional predictive techniques. |
| O6 | Create a realistic execution plan | Allocate 30–35 hours with milestones, dependencies, outputs and quality checks. |

# 3. Public Data Source Strategy

Source selection follows a hierarchy: (1) official Indian government statistics for primary measures; (2) official market systems for transaction/price context; (3) international databases for benchmarking; (4) research institutions for agribusiness and technology context; and (5) academic literature for methods and interpretation. Each dataset should be accompanied by a source URL, access date, coverage period, definition notes and transformation log.

| # | Source | Key data | Relevance | Priority | Access |
| --- | --- | --- | --- | --- | --- |
| 1 | Department of Agriculture & Farmers Welfare — ES&E / DES | Agricultural Statistics at a Glance; crop estimates; MSP-related material; land-use statistics | Primary official source for India-wide agriculture statistics and policy-relevant measures. | High | https://desagri.gov.in/ |
| 2 | DES Area, Production & Yield Reports | State/district/crop/season/year reports for area, production and yield | Core analytical source for crop performance and geographic comparisons. | High | https://data.desagri.gov.in/website/crops-apy-report-web |
| 3 | Open Government Data (data.gov.in) | District-wise, season-wise crop production; agriculture sector datasets/APIs | Machine-readable government datasets; useful for reproducible extraction and analysis. | High | https://data.gov.in/ |
| 4 | e-NAM | Mandi prices, arrivals, traded quantities; historical trade data | Direct market-trend evidence at commodity/APMC/date level. | High | https://www.enam.gov.in/ |
| 5 | FAOSTAT | Production, producer prices, production value and international agriculture indicators | International benchmarking and cross-country/cross-commodity comparisons. | High | https://www.fao.org/faostat/ |
| 6 | World Bank — Agriculture & Rural Development Indicators | Agriculture value added, land, yields, employment and related indicators | Macro-level context and standardized international indicators. | High | https://data.worldbank.org/ |
| 7 | ICAR | Annual reports, publications, crop research programmes and technology developments | Research and agribusiness/technology context; helps connect quantitative trends to innovation. | High | https://www.icar.gov.in/ |
| 8 | MoSPI / NSS | Situation Assessment of Agricultural Households and other NSS reports | Socio-economic context such as farm practices, income, assets, insurance and technology awareness. | High | https://www.mospi.gov.in/ |
| 9 | Academic literature databases | Peer-reviewed agriculture economics, market integration, forecasting and yield studies | Method selection, benchmark variables and interpretation of empirical findings. | Medium | Institution/library databases; Google Scholar/DOI records. |
| 10 | Industry publications | Commodity outlooks, agribusiness reports and market commentary | Contextual signals and hypotheses; use only with source attribution and methodology checks. | Medium | Validate publisher, methodology and publication date. |

Source validation note: The DES site currently lists recent 2025–26 crop-production estimates and 2026–27 MSP material; e-NAM exposes current/historical trade fields including min, modal and max prices, arrivals and traded quantities; data.gov.in provides a large agriculture sector catalogue and APIs. Older datasets remain useful for historical analysis but must not be represented as current observations.

# 4. Research Questions

| ID | Research question |
| --- | --- |
| RQ1 | How have area, production and yield changed for major crops across years, seasons and states? |
| RQ2 | Which crops/states show sustained growth, stagnation or volatility in production and yield? |
| RQ3 | How do mandi arrivals and prices vary by commodity, APMC, state and season? |
| RQ4 | What is the relationship between market arrivals, traded quantity and modal price? |
| RQ5 | Which commodities show the strongest seasonal price volatility? |
| RQ6 | How concentrated is production geographically for selected crops? |
| RQ7 | How do Indian agricultural indicators compare with international benchmarks? |
| RQ8 | What agribusiness/technology developments reported by ICAR and other credible sources may contextualize observed trends? |
| RQ9 | Where do data sources disagree, and can discrepancies be explained by definitions, revisions, coverage or units? |
| RQ10 | Which variables appear promising for later forecasting or predictive modelling, subject to sufficient data quality? |

# 5. KPI Framework

| KPI | Definition | Frequency | Dimensions | Purpose |
| --- | --- | --- | --- | --- |
| Crop production | Production volume (tonnes) | Annual/seasonal | Crop, state, district | Trend and performance |
| Cultivated area | Area under crop (ha) | Annual/seasonal | Crop, geography | Scale and expansion |
| Yield | Production ÷ area (t/ha) | Annual/seasonal | Crop, geography | Productivity |
| YoY growth | (Current − prior) / prior × 100 | Annual | Crop/geography | Growth |
| CAGR | Compound annual growth rate | Multi-year | Crop/geography | Structural trend |
| Market price | Min / modal / max price | Daily/periodic | Commodity/APMC | Market level |
| Price volatility | Std. dev., coefficient of variation, rolling volatility | Daily/weekly/monthly | Commodity/APMC | Risk/instability |
| Arrivals | Commodity arrival quantity | Daily/periodic | Commodity/APMC | Supply flow |
| Traded quantity | Quantity traded/sold | Daily/periodic | Commodity/APMC | Market activity |
| Price spread | Max − min; modal vs benchmark | Daily/periodic | Commodity/APMC | Dispersion |
| Production concentration | Top-state share / HHI where appropriate | Annual | Crop/geography | Geographic concentration |
| Agriculture value added | Current/constant value; % GDP | Annual | India / comparator countries | Macro context |

# 6. Methodology

## 6.1 Phase A — Discovery & Source Validation

Create a source register with owner, URL, access date, coverage, granularity, frequency, format and licensing/usage notes.

Classify each source as primary official, official market, international, research or contextual.

Record the exact dataset/report title and version/date used so the analysis remains reproducible.

Check whether data are revised, provisional, estimated or final and preserve that status.

## 6.2 Phase B — Data Extraction

Prefer API/CSV/XLS downloads where available; use HTML tables or PDF extraction only when machine-readable alternatives are unavailable.

Store raw files unchanged in a raw_data directory and keep processed copies separate.

Use Python (pandas), SQL where useful, and spreadsheet tools for quick inspection.

Create a data dictionary before transformation.

## 6.3 Phase C — Data Cleaning & Quality Assurance

Standardize column names, data types, date formats, crop names, state/APMC names and units.

Check duplicates using natural keys such as date + geography + commodity + market.

Identify missing, zero, negative and implausible values; do not automatically convert missing to zero.

Detect outliers using IQR/z-score/rolling rules and investigate whether they represent real market events or errors.

Reconcile tonnes/quintals/kg, hectares and currency units; document every conversion.

Check temporal continuity and season labels (Kharif/Rabi/other) before aggregating.

Validate selected observations against the original source and perform cross-source checks where definitions overlap.

## 6.4 Phase D — Exploratory & Statistical Analysis

Descriptive statistics: count, mean, median, minimum, maximum, standard deviation and coefficient of variation.

Trend analysis: YoY growth, CAGR, rolling averages and indexed series.

Comparative analysis: crop/state/APMC tables with descriptive interpretation.

Seasonality: monthly/seasonal decomposition where sufficient time-series depth exists.

Market analysis: price-arrival relationships, spreads and volatility.

Geographic comparison: state/district maps if geographic boundaries and identifiers are consistently available.

Correlation analysis as a screening tool; treat correlation as non-causal.

Optional forecasting in later weeks: baseline moving average/naive models, then statistical or ML models if sufficient observations and validation data exist.

## 6.5 Phase E — Reporting

Produce an analytical dataset with a clear data dictionary.

Create charts that directly answer each research question.

Maintain a methodology/readme file and source citation register.

Present limitations beside findings rather than hiding them in an appendix.

# 7. Proposed Analytical Outputs

Agriculture Data Source Register

Clean crop production dataset

Clean market price/arrival dataset

KPI dictionary

Data-quality report

Crop production trend dashboard or notebook

Commodity price/arrival dashboard or notebook

Research findings memo with source-backed observations

Optional forecasting prototype after data sufficiency is confirmed

# 8. 34-Hour Week 1 Timeline

| Phase | Workstream | Hours | Deliverable | Milestone |
| --- | --- | --- | --- | --- |
| 1 | Scope & research framing | 3 | Objectives, scope, research questions | M1 |
| 2 | Government source research | 5 | DES, data.gov.in, e-NAM and MoSPI review | M2 |
| 3 | International/research source research | 3 | FAOSTAT, World Bank, ICAR, academic literature | M2 |
| 4 | Dataset profiling plan | 4 | Granularity, variables, units, coverage, access methods | M3 |
| 5 | KPI & research-question mapping | 3 | Map questions to measurable indicators | M3 |
| 6 | Methodology design | 5 | Extraction, cleaning, validation, analysis workflow | M4 |
| 7 | Risk & quality framework | 3 | Data quality, access, comparability and reproducibility risks | M5 |
| 8 | Timeline/resource plan | 2 | Work breakdown and dependencies | M5 |
| 9 | Report writing & formatting | 4 | Compile findings, tables and appendices | M6 |
| 10 | QA & packaging | 2 | Check links, references, structure and files | M6 |

Total planned effort: 34 hours. This sits within the required 30–35 hour range and reserves 2 hours for final QA/package integrity.

# 9. Resource Allocation

| Resource type | Resource | Allocation | Purpose |
| --- | --- | --- | --- |
| Human | Intern / Data Analyst | 34 hours | Research, extraction design, cleaning specification, analysis planning and documentation. |
| Technical | Python + pandas | As required | Data extraction/cleaning/EDA and reproducible scripts. |
| Technical | Excel / spreadsheet tool | As required | Quick profiling, validation and stakeholder-friendly tables. |
| Technical | SQL (optional) | As required | Structured storage/querying when datasets become larger. |
| Visualization | Power BI / Tableau / Python plotting | Later phase | Dashboard and communication layer. |
| Reference | Government portals / reports | Core | Primary evidence and definitions. |
| Reference | Academic literature | Supporting | Method selection and contextual interpretation. |

# 10. Risk Assessment & Mitigation

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Data access changes / portal downtime | Medium | High | Maintain source register; save permitted raw downloads; document access date; use official alternate endpoints where available. |
| R2 | Missing or inconsistent observations | High | High | Profile missingness before analysis; use explicit missing codes; avoid silent imputation; document any justified method. |
| R3 | Different definitions across sources | High | High | Create data dictionary; compare metadata; harmonize only after confirming conceptual equivalence. |
| R4 | Provisional vs final estimates | Medium | High | Tag estimate status and revision date; do not mix without disclosure. |
| R5 | Unit/currency mismatch | Medium | High | Store original unit plus standardized unit; validate conversion formulas. |
| R6 | Outliers caused by real events | Medium | Medium | Investigate before removal; compare with source notes and adjacent observations. |
| R7 | Low granularity for some indicators | Medium | Medium | Use aggregation appropriate to the source; avoid false precision; identify data gaps as findings. |
| R8 | Overinterpretation/correlation ≠ causation | Medium | High | Use cautious language; reserve causal analysis for designs that support it. |
| R9 | Reproducibility problems | Medium | High | Maintain raw/processed separation, source log, code/readme, version/date and transformation log. |
| R10 | Scope expansion | Medium | Medium | Freeze Week 1 scope; prioritize high-value datasets and defer optional modelling. |

# 11. Quality & Evaluation Criteria

Clarity: every objective maps to a measurable output.

Depth: source inventory covers government, market, international, research and contextual evidence.

Feasibility: methods are realistic for public data and the available 30–35 hour Week 1 window.

Reproducibility: sources, dates, definitions, transformations and assumptions are documented.

Analytical validity: metrics are defined before analysis and causal claims are avoided unless justified.

Time management: 34 hours are explicitly allocated across research, methodology, risk, documentation and QA.

Future usefulness: outputs create reusable foundations for later data collection, EDA, modelling and dashboard work.

# 12. Week 1 Milestones & Acceptance Criteria

| Milestone | Acceptance criterion |
| --- | --- |
| M1 | Research scope frozen |
| M2 | Source map completed |
| M3 | KPI framework completed |
| M4 | Methodology approved |
| M5 | Risk register completed |
| M6 | Final package QA |

# 13. Recommended Week 2 Handoff

Select 1–2 crop families and 3–5 commodities for a focused pilot analysis.

Download and preserve raw DES/data.gov.in crop statistics and e-NAM market data for the selected scope.

Create a standardized data dictionary and validation rules.

Perform exploratory data analysis and generate the first trend/market charts.

Document data gaps discovered during extraction and revise the research questions only where necessary.

Begin a reproducible notebook/script structure so later analysis can be rerun with refreshed data.

# 14. Source Notes & References

Department of Agriculture & Farmers Welfare, ES&E Division — Agriculture Statistics at a Glance and current agricultural estimates/MSP publications. https://desagri.gov.in/

DES — Area, Production & Yield Reports. https://data.desagri.gov.in/website/crops-apy-report-web

Government of India OGD Platform — Agriculture sector catalogue and district-wise season-wise crop production datasets. https://data.gov.in/sector/agriculture

e-NAM — Trade details, historical trade data and price dashboards. https://www.enam.gov.in/

FAO — FAOSTAT agricultural production/value and producer-price data resources. https://www.fao.org/faostat/

World Bank — World Development Indicators: Agriculture & Rural Development. https://data.worldbank.org/

ICAR — Annual reports, publication catalogue and coordinated agricultural research projects. https://www.icar.gov.in/

MoSPI / NSSO — Situation Assessment of Agricultural Households and NSS reports. https://www.mospi.gov.in/

# Appendix A — Data Dictionary Starter

| Field | Meaning | Type | Rule |
| --- | --- | --- | --- |
| date/year | Time dimension | Date/year | Normalize to ISO date or integer year. |
| state | Geographic dimension | Text | Use a controlled state master. |
| district | Geographic dimension | Text | Validate spelling/renaming across years. |
| crop | Crop dimension | Text | Map source-specific crop names to canonical names. |
| season | Season | Text | Kharif/Rabi/other; preserve source value. |
| area_ha | Crop area | Numeric | Hectares; retain original field separately. |
| production_tonnes | Production | Numeric | Tonnes; verify source unit. |
| yield_t_per_ha | Productivity | Numeric | Production / area where definition permits. |
| commodity | Market dimension | Text | Canonical commodity name. |
| apmc | Market dimension | Text | Controlled market/APMC identifier. |
| min_price | Market price | Numeric | Retain source currency/unit. |
| modal_price | Market price | Numeric | Preferred central market price measure where appropriate. |
| max_price | Market price | Numeric | Retain source currency/unit. |
| arrival_qty | Market supply | Numeric | Retain source unit. |
| traded_qty | Market activity | Numeric | Retain source unit. |
| source_date | Provenance | Date | Date data/report was accessed or downloaded. |

# Appendix B — Submission Checklist

Main DOCX opens correctly and contains all required sections.

Research questions are specific and measurable.

Public data sources are identified and their relevance is justified.

Data extraction and cleaning methodology is documented.

KPI framework is included.

34-hour timeline is included and totals 30–35 hours.

Milestones and risk mitigation are included.

References contain official source names and access links.

Supporting files are organized in clearly named folders.

Raw/processed data are separated when actual datasets are subsequently downloaded.